# WORK BREAKDOWN

# AND

# RESPONSIBILITIES

Documentary Evidence of Teamwork Plan and Schedule

# 1. Work Breakdown Structure

| Task ID | Task Description | Subtasks |
| --- | --- | --- |
| 1.0 | Literature Review | 1.1 Conduct need analysis & problem identification (evidence: interviews/survey/field data) 1.2 Review research papers related to the problem/technology (min. 3) 1.3 Review existing products/technologies (min. 2) 1.4 Review relevant patents (min. 1; or open-source repos for software-only projects) 1.5 Complete gap analysis; finalize problem statement & project title |
| 2.0 | Requirements & Constraints | 2.1 Define functional requirements (5–8) and performance requirements (3–5) 2.2 Identify applicable engineering standards and codes 2.3 Document design constraints (economic, environmental, manufacturability, ethical/safety, social, regulatory) with reasons where not applicable 2.4 Map SDGs addressed; complete data ethics & management (if applicable) |
| 3.0 | Concept Development & Alternatives | 3.1 Identify 2–3 genuinely different candidate design approaches 3.2 Evaluate approaches (Comparison of Alternatives or Trade-off Analysis table) 3.3 Select final design with justification; assess novelty, IP overlap, and TRL |
| 4.0 | Final Design & Implementation | 4.1 Define system architecture (subsystem breakdown, interfaces) 4.2 Prepare work plan: timeline/Gantt and risk assessment 4.3 Individual module design, development, and initial Budget/BoM 4.4 System integration (combine modules; revise BoM if substitutions occur) |
| 5.0 | Testing & Evaluation | 5.1 Module-level testing against individual specs 5.2 System-level integration testing 5.3 Evaluate results against requirements (traceability matrix); finalize BoM 5.4 Iterate: if requirements aren't met, revise design (Task 4.0) and re-test until criteria are satisfied |
| 6.0 | Report Writing & Final Presentation | 6.1 Compile report chapters and appendices 6.2 Complete broader-impact analysis (ethics, sustainability/SDGs, commercialization) 6.3 Prepare slides and demo for final defence |

# 2. Team Responsibility Matrix

| ID | Subtask | Responsible Member Register Number(s) |
| --- | --- | --- |
| 1.0 | Literature Review |  |
| 1.1 | Conductneed analysis & problem identification (evidence: interviews/survey/field data) | S.Yashika 9923005281 |
| 1.2 | Review research papers related to the problem/technology (min. 3) | S.Abarna 9923005233 |
| 1.3 | Review existing products/technologies (min. 2) | Animala gurusainath 9923005003 |
| 1.4 | Review relevant patents (min. 1; or open-source repos for software-only projects) | S.Abarna 9923005233 |
| 1.5 | Complete gap analysis; finalize problem statement & project title | S.yashika 9923005281 |
| 2.0 | Requirements & Constraints |  |
| 2.1 | Define functional requirements (5–8) and performance requirements (3–5) | S.Abarna 9923005233 |
| 2.2 | Identify applicable engineering standards and codes | S.yashika 9923005281 |
| 2.3 | Document design constraints (economic, environmental, manufacturability, ethical/safety, social, regulatory) with reasons where not applicable | S.Abarna 9923005233 |
| 2.4 | Map SDGs addressed; complete data ethics & management (if applicable) | Animala gurusainath 9923005003 |
| 3.0 | Concept Development & Alternatives |  |
| 3.1 | Identify 2–3 genuinely different candidate design approaches | S.yashika 9923005281 |
| 3.2 | Evaluate approaches (Comparison of Alternatives or Trade-off Analysis table) | S.Abarna 9923005233 |
| 3.3 | Select final design with justification; assess novelty, IP overlap, and TRL | S.yashika 9923005281 |
| 4.0 | Final Design & Implementation |  |
| 4.1 | Define system architecture (subsystem breakdown, interfaces) | S.Abarna 9923005233 |
| 4.2 | Prepare work plan: timeline/Gantt and risk assessment | S.yashika 9923005281 |
| 4.3 | Individual module design, development, and initial Budget/BoM | Animala gurusainath 9923005003 |
| 4.4 | System integration (combine modules; revise BoM if substitutions occur) | S.yashika 9923005281 |
| 5.0 | Testing & Evaluation |  |
| 5.1 | Module-level testing against individual specs | Animala gurusainath 9923005003 |
| 5.2 | System-level integration testing | S.yashika 9923005281 |
| 5.3 | Evaluate results against requirements (traceability matrix); finalize BoM | S.Abarna 9923005233 |
| 5.4 | Iterate: if requirements aren't met, revise design (Task 4.0) and re-test until criteria are satisfied | Animala gurusainath 9923005003 |
| 6.0 | Report Writing & Final Presentation |  |
| 6.1 | Compile report chapters and appendices | S.Abarna 9923005233 |
| 6.2 | Complete broader-impact analysis (ethics, sustainability/SDGs, commercialization) | S.Yashika 9923005281 |
| 6.3 | Prepare slides and demo for final defence | Animalagurusainath 9923005003 |

# 3. Timeline / Gantt Chart

| Week | 1.0 Lit. Review | 2.0 Requirements | 3.0 Concept Dev. | 4.0 Design/Impl. | 5.0 Testing | 6.0 Reporting |
| --- | --- | --- | --- | --- | --- | --- |
| W1 | X |  |  |  |  |  |
| W2 | X | X |  |  |  |  |
| W3 |  | X | X |  |  |  |
| W4 |  |  | X | X |  |  |
| W5 |  |  |  | X |  |  |
| W6 |  |  |  | X |  |  |
| W7 |  |  |  | X | X |  |
| W8 |  |  |  | X | X |  |
| W9 |  |  |  | X | X |  |
| W10 |  |  |  |  | X | X |
| W11 |  |  |  |  | X | X |
| W12 |  |  |  |  |  | X |

Team Declaration and Guide Endorsement

We confirm that the task breakdown, responsibilities, and timeline above reflect our team's genuine plan. We also confirm that if any AI tool was used while preparing this document (e.g., to search, summarize, or draft text), its use is disclosed below, and our team has personally verified and understood the content rather than copying it as-is.

| AI Tool(s) Used (if any) & For What | Claude - Paper summary & Problem statement Gemini - Design ideas & Requirements Google - Papers, Products search |
| --- | --- |

| Team Member Name | Register Number | Signature |
| --- | --- | --- |
| S.ABARNA | 9923005233 |  |
| S.YASHIKA | 9923005281 |  |
| ANIMALA GURUSAINATH | 9923005003 |  |

### Guide's Review Comments (mandatory — not a signature-only field):

| Date of Submission |  |
| --- | --- |
| Guide Name |  |
| Guide Signature |  |